## Slide 1
Meridian Defense Systems C2 Platform Program
Weekly Leadership Summary: Milestones, Risks and Status Accuracy
Meridian Defense Systems | Report date 2026-09-24

## Slide 2
One of three open milestones has an unsupported status
Meridian Defense Systems C2 Platform | Weekly status as of 2026-09-24
2
1 of 4
milestones with reported status Complete
+14 days
ATO forecast 2026-10-14 vs. 2026-09-30 plan
1 of 3
open milestones whose reported status the evidence does not support
ATO: ATO Approval Delayed by ISSO Review. Behind schedule.
CDR: CDR Status Should Be Corrected. Off track, dependency overdue.
DEMO: IOC Readiness Review On Track. Watch unassigned dry-run task.

## Slide 3
Milestone schedule and evidence check
Statuses from the milestone sheet; evidence check from the weekly report
Meridian Defense Systems C2 Platform | Weekly status as of 2026-09-24
3
Milestone | Planned | Forecast / actual | Reported status | Evidence supports status?
Preliminary Design Review (PDR) | 2026-04-15 | 2026-04-15 | Complete | Not assessed this week
Authority to Operate (ATO) Approval | 2026-09-30 | 2026-10-14 | At Risk | Yes
Critical Design Review (CDR) | 2026-11-15 | 2026-11-15 | On Track | No
Customer Demo / IOC Readiness Review | 2026-12-01 | TBD | Not Started | Yes
Reported status comes from the milestone sheet. The evidence check comes from the approved weekly report.

## Slide 4
Is the reported status accurate?
1 of 3 open milestones has a reported status the evidence does not support
Meridian Defense Systems C2 Platform | Weekly status as of 2026-09-24
4
ATO
Reported
Evidence supports
At Risk
Yes
Cybersecurity ATO documentation task overdue since 2026-09-10, blocked pending ISSO review.
Forecast slipped to 2026-10-14, about two weeks past the 2026-09-30 plan.
Consistent with the ISSO office's informal estimate of a 2-3 week delay.
CDR
Reported
Evidence supports
On Track
No
Radar feed adapter integration, a direct CDR dependency, was due 2026-09-12 and remains in progress as of 2026-09-24.
At least another week of delay expected: vendor API documentation is incomplete.
CDR is planned for 2026-11-15, so some runway remains.
The reported On Track status should be corrected.
DEMO
Reported
Evidence supports
Not Started
Yes
Report states on track for 2026-12-01.
Test plan update in progress, due 2026-09-24.
Dry-run logistics, due 2026-10-01, has no assignee despite the customer's explicit request.

## Slide 5
Two overdue items and one unassigned task are named in the report
Meridian Defense Systems C2 Platform | Weekly status as of 2026-09-24
5
Item | Milestone | Type | What the report says
Cybersecurity ATO documentation task overdue, blocked pending ISSO review | ATO | Issue | Overdue since 2026-09-10; forecast now 2026-10-14
Radar feed adapter integration overdue; vendor API documentation incomplete | CDR | Issue | Due 2026-09-12; at least another week of delay expected
Dry-run logistics task has no assignee | DEMO | Issue | Due 2026-10-01; customer explicitly requested the dry run
Closed and can be removed from the risk register: RISK-021 (subcontractor staffing gap on fusion engine team).

## Slide 6
Four tasks are named in the report
Meridian Defense Systems C2 Platform | Weekly status as of 2026-09-24
6
Task | Milestone | Due | Status as stated
Cybersecurity ATO documentation | ATO | 2026-09-10 | Overdue, blocked pending ISSO review
Radar feed adapter integration | CDR | 2026-09-12 | In progress, overdue
Test plan update | DEMO | 2026-09-24 | In progress, due 2026-09-24
Dry-run logistics | DEMO | 2026-10-01 | No assignee

## Slide 7
Proposed decisions and asks
Meridian Defense Systems C2 Platform | Weekly status as of 2026-09-24
7
1
Correct the CDR status in the tracker
CDR: the report says the reported On Track status should be corrected.
2
Track the DEMO dry-run logistics task closely
DEMO: due 2026-10-01 with no assignee; the report says to track it closely.
3
Remove RISK-021 from the risk register
CDR: the report says the closed risk can be removed.