## Slide 1
Meridian Defense Systems C2 Platform
Weekly Leadership Summary: Milestones, Risks and Status Accuracy
Report date: 2026-09-24

## Slide 2
One of three open milestones has an unsupported status
1/4
Milestones reported Complete
14 days
Largest forecast slip (ATO)
1
Open milestones with unsupported status
• ATO: ATO Approval Delayed by ISSO Review
• CDR: CDR Status Should Be Corrected
• DEMO: IOC Readiness Review On Track
Meridian Defense Systems C2 Platform | Weekly status as of 2026-09-24
2

## Slide 3
Milestone schedule: one of four milestones is complete
Milestone | Planned | Forecast / Actual | Reported status | Evidence supports status?
Preliminary Design Review (PDR) | 2026-04-15 | 2026-04-15 | Complete | Not assessed this week
Authority to Operate (ATO) Approval | 2026-09-30 | 2026-10-14 | At Risk | Yes
Critical Design Review (CDR) | 2026-11-15 | 2026-11-15 | On Track | No
Customer Demo / IOC Readiness Review | 2026-12-01 | TBD | Not Started | Yes
Reported statuses come from the milestone sheet; the evidence assessment comes from this week's approved report.
Meridian Defense Systems C2 Platform | Weekly status as of 2026-09-24
3

## Slide 4
Two of three open milestone statuses are supported by evidence
ATO Approval Delayed by ISSO Review
Reported: At Risk
Evidence supports status: Yes
• Cybersecurity ATO documentation task overdue since 2026-09-10, blocked pending ISSO review
• Forecast slipped to 2026-10-14, about two weeks past the 2026-09-30 plan
• ISSO office's informal estimate is a 2-3 week delay
CDR Status Should Be Corrected
Reported: On Track
Evidence supports status: No
• Radar feed adapter integration (a CDR dependency) was due 2026-09-12 and remains in progress as of 2026-09-24
• Team expects at least another week of delay due to incomplete vendor API documentation
• CDR is planned for 2026-11-15, so some schedule runway remains
• Reported "On Track" status should be corrected to reflect this overdue, dependency-linked work
IOC Readiness Review On Track
Reported: Not Started
Evidence supports status: Yes
• On track for its 2026-12-01 date
• Test plan update is in progress and was due 2026-09-24
• Customer-requested dry-run logistics task is not due until 2026-10-01
• Dry-run logistics task still has no assignee despite the customer's explicit request
Meridian Defense Systems C2 Platform | Weekly status as of 2026-09-24
4

## Slide 5
Three overdue or unassigned items are named across two milestones
Item | Milestone | Type | What the report says
Cybersecurity ATO documentation task | ATO | Not stated | Overdue since 2026-09-10; blocked pending ISSO review
Radar feed adapter integration task | CDR | Not stated | Due 2026-09-12; still in progress; ~1 more week of delay expected (vendor API documentation incomplete)
Dry-run logistics task | DEMO | Not stated | No assignee despite customer request; due 2026-10-01
RISK-021 (Subcontractor staffing gap on fusion engine team) — Closed; recommended for removal from the risk register (CDR).
Meridian Defense Systems C2 Platform | Weekly status as of 2026-09-24
5

## Slide 6
Four named tasks drive this week's schedule and assignment watch items
Task | Milestone | Due date | Status
Cybersecurity ATO documentation task | ATO | 2026-09-10 | Overdue; blocked pending ISSO review
Radar feed adapter integration | CDR | 2026-09-12 | In progress (overdue); vendor API documentation incomplete
Test plan update | DEMO | 2026-09-24 | In progress
Dry-run logistics task | DEMO | 2026-10-01 | Not yet due; no assignee
Meridian Defense Systems C2 Platform | Weekly status as of 2026-09-24
6

## Slide 7
Three decisions are proposed: one status correction, one removal, one watch item
CDR
Correct CDR's reported status from "On Track" to reflect the overdue, dependency-linked radar feed adapter integration task.
CDR
Remove RISK-021 (subcontractor staffing gap, fusion engine team) from the risk register; it is closed.
DEMO
Track the unassigned dry-run logistics task closely as its 2026-10-01 due date nears.
Meridian Defense Systems C2 Platform | Weekly status as of 2026-09-24
7