## Milestones
Milestone | Planned Date | Forecast/Actual Date | Status
Preliminary Design Review (PDR) | 2026-04-15 | 2026-04-15 | Complete
Authority to Operate (ATO) Approval | 2026-09-30 | 2026-10-14 | At Risk
Critical Design Review (CDR) | 2026-11-15 | 2026-11-15 | On Track
Customer Demo / IOC Readiness Review | 2026-12-01 | TBD | Not Started